## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Data Analytics
INTERN NAME: | Amit Kumar Pandey
PROJECT NAME: | Student Performance and Career Insights Analysis
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 29-05-2026

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | AI Project Management Assistant
PROJECT ID | GPI-AI-2026
PROJECT MANAGER | Tushar Sharma
PROJECT SPONSOR | Cloud Counselage / CC-GAC Foundation
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 2026-05-16 | Gemini API key was invalid during integration | AI Integration | Yes | Verify API key before implementation | Generated new API key and validated configuration | Tushar Sharma | SOLVED | ntegration completed successfully
2 | 2026-05-18 | Gemini free tier quota exceeded | API Management | Yes | Monitor API usage and maintain backup provider | Migrated to OpenRouter API | Tushar Sharma | SOLVED | Improved API reliability
3 | 2026-05-20 | PowerShell execution policy blocked npm commands | Development Environment | Yes | Configure PowerShell execution policy before setup | Update execution policy settings | Tushar Sharma | SOLVED | Development environment stabilized
4 | 2026-05-23 | OpenRouter image analysis returned errors | AI Integration | Yes | Validate image handling workflow | Fixed image upload and API request structure | Tushar Sharma | SOLVED | Image analysis working properly
5 | 2026-05-26 | Chat history was not being stored | Feature Development | Yes | implement local storage/session management | Added project storage functionality | Tushar Sharma | SOLVED | Better user experience
6 | 2026-05-29 | React component import errors caused build failures | Development | Yes | Verify imports and file structure regularly | Fixed component paths and imports | Tushar Sharma | SOLVED | Build completed successfully
7 | 2026-05-31 | PDF export feature required additional libraries | Feature Development | No | Research dependencies before implementation | Installed and configured PDF libraries | Tushar Sharma | SOLVED | Export functionality added
8 | 2026-06-03 | Deployment configuration issues on Vercel | Deployment | No | Test production build before deployment | Fixed build configuration and redeployed | Tushar Sharma | SOLVED | Application deployed successfully
9 | 2026-06-04 | Large AI responses affected UI rendering | Performance Optimization | No | Optimize rendering and response handling | Improved response processing logic | Tushar Sharma | SOLVED | Faster user experience
10 | 2026-06-05 | Final testing revealed minor UI inconsistencies | Testing & QA | No | Conduct complete testing before submission | Fixed UI alignment and responsiveness | Tushar Sharma | SOLVED | Professional final submission