## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | AI Project Management Assistant
PROJECT SPONSOR | Cloud Counselage Pvt. Ltd.
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 2026-05-14
EXPECTED COMPLETION DATE | 2026-06-05
ESTIMATED COST | N.A. (Academic Internship Project)
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE | The objective of this project is to develop an AI Project Management Assistant that helps users automate project planning, task generation, risk analysis, documentation, and project management activities. The platform uses Artificial Intelligence to improve productivity, reduce manual effort, and assist in project decision-making.
BUSINESS CASE | Project managers and teams spend significant time performing repetitive project management tasks such as planning, documentation, task creation, and risk assessment. This project introduces AI-powered automation to simplify these activities and improve efficiency, allowing users to focus on strategic project execution rather than administrative work.
GOALS/METRICS | The project aims to successfully provide AI-powered project assistance, image analysis, task generation, risk analysis, and project documentation support. Success will be measured through successful AI integration, accurate outputs, responsive user experience, successful deployment, and completion of all internship deliverables.
EXPECTED DELIVERABLES | AI Project Management Assistant Application AI Chat Assistant Image Analysis Module Project Dashboard Task Generator Mind Map Generator Architecture Generator Risk Analysis Module PDF Export Feature GitHub Repository Vercel Deployment Project Documentation SRS Document Project Charter RAID Log Project Schedule WBS Document Final Project Report
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE | The project includes development of a web-based AI Project Management Assistant using React, Vite, and OpenRouter API. The scope covers AI chat functionality, image analysis, project planning assistance, task generation, risk analysis, PDF export, dashboard development, project documentation, testing, deployment, and project reporting.
OUTSIDE OF SCOPE | The project does not include enterprise-level user management, role-based access control, real-time team collaboration, payment integration, advanced analytics dashboards, mobile application development, or custom AI model training. These may be considered in future enhancements.
PROJECT RESOURCES AND COSTS
PROJECT TEAM | 1 (Tushar Sharma)
SUPPORT RESOURCES | Cloud Counselage Pvt. Ltd. Internship Mentor OpenRouter API GitHub Vercel Internet Resources
COST ALLOCATION | Development Cost: N.A. Hosting: Free Tier (Vercel) Version Control: GitHub AI Services: OpenRouter API Total Cost: N.A. (Academic Internship Project)
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER | Tushar Sharma
KEY STAKEHOLDERS | Cloud Counselage Pvt. Ltd. Internship Mentor Project Manager End Users Project Developer (Tushar Sharma)
END CUSTOMER | Project Managers Software Development Teams Students Business Users Organizations requiring project management assistance
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS | API quota limitations Third-party API downtime Deployment issues Internet dependency Integration challenges Browser compatibility issues Performance issues with large AI responses
ASSUMPTIONS | Users have internet access. OpenRouter API remains available. Users provide valid project-related information. Modern browsers are available. Required development tools remain accessible throughout the project.
CONSTRAINTS | Limited internship duration. Dependence on third-party AI APIs. Internet connectivity requirements. Free-tier API limitations. Limited project budget. Deployment platform restrictions.
MILESTONES
MILESTONE 1- Requirement Gathering | Completion Date: 15-05-2026 Requirements, objectives, scope, and stakeholder expectations were identified and documented.
MILESTONE 2 - Planning | Completion Date: 17-05-2026 Project schedule, WBS, SRS, and project planning activities were completed.
MILESTONE 3 - Design | Completion Date: 19-05-2026 UI/UX design, architecture planning, and project workflow design were completed.
MILESTONE 4 - Development | Completion Date: 30-05-2026 Dashboard, AI chat, image analysis, task generation, and project management features were developed.
MILESTONE 5 - Testing | Completion Date: 03-06-2026 Functional testing, integration testing, debugging, and performance validation were completed.
MILESTONE 6 - Deployment | Completion Date: 04-06-2026 Application was deployed successfully on Vercel and GitHub repository was finalized.
MILESTONE 7 - Closure | Completion Date: 05-06-2026 Final documentation, reports, RAID Log, WBS, SRS, and project submission were completed successfully.