## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 2 | 0 | 1 | 0 | 0 | 0
| Project title: | AI Project Management Assistant |  | Project Id: | GPI-AI-2026 | Project Manager: | Harshada Topale |  |  | Assumption | 2 | 0 | 1 | 0 | 0 | 0
[10 empty] | Issue | 2 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: | 1 |  | Last Updated date: | 2026-06-05 | Project Team Lead: | Tushar Sharma |  |  | Dependency | 2 | 0 | 1 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 8 |  |  |  |  | 3
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | OpenRouter API quota exhausted during project usage | AI responses will stop working | Monitor API usage and maintain backup API keys | Tushar Sharma | High | 6 | Open | Risk
2 | Risk | Deployment failure on Vercel | Application becomes inaccessible | Test build locally before deployment | Tushar Sharma | Moderate | 4 | Closed | Assumption
3 | Assumption | Users have stable internet connection | Application features require internet access | Inform users about connectivity requirements | Tushar Sharma | High | 5 | open | Issue
4 | Assumption | OpenRouter API remains available throughout project lifecycle | AI functionality depends on API availability | Monitor API provider status regularly | Tushar Sharma | Low | 2 | closed | Dependency
5 | Issue | API integration errors during development | Delayed feature implementation | Debug API requests and validate configurations | Tushar Sharma | Moderate | 3 | closed
6 | Issue | Large response processing causes performance lag | Slower user experience | Optimize frontend rendering and response handling | Tushar Sharma | Low | 2 | closed | Open
7 | Dependency | Project depends on OpenRouter API services | AI module cannot function without API | Maintain valid API key and fallback plan | Tushar Sharma | High | 5 | Open | Closed
8 | Dependency | Project depends on React, Vite and external libraries | Missing packages may break application | Verify dependencies before deployment | Tushar Sharma | Moderate | 3 | closed
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24